## GRAFIK
DAILY SLA AVG BULAN DESEMBER 2025
Baterai | Total Site | AVG SLA
Talis5 Full | 19 | 92.73%
Talis5 Mix | 15 | 81.49%
JS PRO | 46 | 91.64%
TOTAL | 80 | 90.69%
Baterai | Penyebab AVG SLA masih dibawah 95.5%
Talis5 Full | SNMP DOWN
Talis5 Mix | Problem VSAT SNMP DOWN
JS PRO | Insiden terbakar Problem Vsat
History GAMAS (Gangguan Masal)
-
*Tracking SLA avg daily bulan Desember 2025*
Tgl 1 - 8 /12/2025 |  |  | 2025-12-08 | 8 | Tgl 1 -
*80 site* | *90,69%* |  | 90.6882 | 12
Talis5 Full | *92,73%* |  | 92.7301 | 2025
Talis5 Mix | *81,49%* |  | 81.4855
JS PRO | *91,64%* |  | 91.6382
Trend SLA avg Bulan Desember 2025
Minggu 1 | 90.69%
Minggu 2 | #DIV/0!
Minggu 3 | #DIV/0!
Minggu 4 | #DIV/0!

## SLA
[9 empty] | https://docs.google.com/spreadsheets/d/1klpLbbl5DSHbiNwz8jHPLPE8mhHRawTOKn795joTXFw/edit?usp=sharing | https://docs.google.com/spreadsheets/d/1kKhKU9XrjDhGOu5EkNUWQOZ1ZrPel-YbUb4bQ-yS45E/edit?usp=sharing | https://docs.google.com/spreadsheets/d/14NdKGXXCTg0qub1jKzLHUFBr4zihZv7E8Opl8Qs-mVQ/edit?usp=sharing | https://docs.google.com/spreadsheets/d/1n0dpf0G-7VNAgPCdli5FretXgDsHqInvDDuy18Q4GxU/edit?usp=sharing | https://docs.google.com/spreadsheets/d/1S1w4agYvLlhtsLplO3baSIN0JNorp1EPIBYmH8eocHE/edit?usp=sharing | https://docs.google.com/spreadsheets/d/1oZzSU9oXVKRbWr-FIVz676poc89Gcv_l5o6W2jydiUs/edit?usp=sharing | https://docs.google.com/spreadsheets/d/1SvfV6O2h_kUIZJJu5ZqtVGE-LAFnD2jb_RyFIq-aVU0/edit?usp=sharing
[7 empty] | 90.69% |  | 87.71% | 89.14% | 90.1% | 89.69% | 91.27% | 93.41% | 93.5%
NAMA SITE | PROVINSI | KODE SITE | BATERAI TYPE | Done Instal (Talis) | PIC | PROBLEM | SLA AVG | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
MENARBU | PAPUA BARAT | JS27 | Talis5 Mix | 2025-10-08 |  | Vsat up down | 96.38% |  | 87.71% 1: 85.42%; 89.14% 2: 97.91%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 94.1%; 93.41% 6: 97.57%; 93.5% 7: 99.65%
ISENEBUAI | PAPUA BARAT | JS31 | Talis5 Full | 2024-11-30 |  | SNMP sudah up (Done replace ehub) | 99.9% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 99.65%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 99.65%
BOHA | PAPUA SELATAN | JS01 | Talis5 Mix | 2025-11-13 |  | SOMO POWER , Vsat sudah up, SNMP problem. done revit tgl 13-nov-25 site up snmp sudah up | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
KOBROR | MALUKU | JS33 | Talis5 Full | 2025-10-06 |  | Done revit tgl 6/10/25 | 99.8% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 98.61%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
YABORE | PAPUA BARAT | JS17 | Talis5 Mix | 2025-10-06 | VSAT | VSAT masih down , Done revit tgl 6/10/25 | 0% | Potensi SP | bar: 87.71% 1 to 93.5% 7
INYORA | PAPUA BARAT | JS19 | JS PRO |  | VSAT | VSAT masih down | 0% | Potensi SP | bar: 87.71% 1 to 93.5% 7
SUMAE | MALUKU UTARA | JS12 | JS PRO |  |  | Vsat sudah up | 99.85% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 98.96%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
TABANGAME | MALUKU UTARA | JS13 | Talis5 Mix (Migrasi pln) | 2025-11-12 |  | SOMO BTS , power up down done revit tgl 12-nov-25 | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
HUKUKECIL | MALUKU | JS43 | Talis5 Mix | 2025-11-07 | VSAT | vsat sudh up | 45.45% | Potensi SP | 87.71% 1: 0%; 89.14% 2: 0%; 90.1% 3: 58.43%; 89.69% 4: 47.12%; 91.27% 5: 25.79%; 93.41% 6: 86.8%; 93.5% 7: 100%
RENIS | PAPUA BARAT | JS61 | JS PRO |  | VSAT | Vsat up down sudah stabil | 81.05% |  | 87.71% 1: 60.11%; 89.14% 2: 78.08%; 90.1% 3: 79.21%; 89.69% 4: 49.96%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
ELIASA | MALUKU | JS34 | Talis5 Mix | 04 March 2025 |  | SNMP sudah up | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
HONITETU | MALUKU | JS42 | Talis5 Mix (Migrasi pln) | 2025-10-30 |  | SNMP sudah up | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
AISA | PAPUA BARAT | JS69 | JS PRO |  |  | Vsat sudah up | 99.85% |  | 87.71% 1: 99.65%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 99.3%; 93.41% 6: 100%; 93.5% 7: 100%
KOREWATARA | PAPUA BARAT | JS87 | JS PRO |  |  | SNMP sudah up | 99.9% |  | 87.71% 1: 100%; 89.14% 2: 99.65%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 99.65%
OCIMALOLEO | MALUKU UTARA | JS127 | JS PRO |  | VSAT | vsat sudah up | 88.19% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 65.56%; 91.27% 5: 51.8%; 93.41% 6: 100%; 93.5% 7: 100%
WAYATIM | MALUKU UTARA | JS10 | JS PRO |  |  | Sudah up | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
WARLOI | MALUKU | JS28 | JS PRO |  |  | SNMP sudah up | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
RUMOY | MALUKU | JS97 | Talis5 Full | 12 December 2024 | POWER-Tiket-onprogres | SNMP masih down | 0% | Potensi SP | bar: 87.71% 1 to 93.5% 7
BORI | PAPUA BARAT | JS50 | JS PRO |  |  | Insiden Power Terbakar (Done donor), site sudah up | 98.07% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 99.65%; 89.69% 4: 86.8%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
MAKARORO | PAPUA BARAT | JS76 | Talis5 Full | 15 December 2024 | POWER | SNMP up down | 75.63% |  | 87.71% 1: 0%; 89.14% 2: 63.8%; 90.1% 3: 100%; 89.69% 4: 75.69%; 91.27% 5: 89.93%; 93.41% 6: 100%; 93.5% 7: 100%
MAWE | PAPUA BARAT | JS53 | JS PRO |  |  |  | 99.95% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 99.65%; 93.41% 6: 100%; 93.5% 7: 100%
KAMPUNG BARU 1 | MALUKU UTARA | JS8 | JS PRO |  |  | SNMP sudah UP | 99.9% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 99.31%; 93.41% 6: 100%; 93.5% 7: 100%
NIAP | PAPUA BARAT | JS26 | Talis5 Full | 04 August 2025 |  | SNMP sudah UP | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SILANG | MALUKU UTARA | JS07 | Talis5 Mix | 16 January 2025 |  | SNMP sudah UP | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SEKELY | MALUKU UTARA | JS119 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SOROWAN | PAPUA BARAT | JS89 | Talis5 Full | 14 December 2024 |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
TUTUPA | MALUKU UTARA | JS16 | JS PRO |  |  | VSAT sudah up | 99.8% |  | 87.71% 1: 99.65%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 98.96%; 93.41% 6: 100%; 93.5% 7: 100%
BOLDON | PAPUA BARAT | JS86 | JS PRO |  |  | Vsat Sudah up | 96.97% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 78.82%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SAYORI SIKAMA | PAPUA BARAT | JS23 | Talis5 Full | 06 August 2025 |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
NANIMORI | PAPUA BARAT | JS11 | Talis5 Full | 10 August 2025 |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
MARANTUTUL | MALUKU | JS47 | JS PRO |  |  |  | 99.95% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 99.65%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
TABAJAYA | MALUKU UTARA | JS14 | JS PRO |  |  |  | 99.55% |  | 87.71% 1: 97.22%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 99.65%; 93.41% 6: 100%; 93.5% 7: 100%
SOBIAR | PAPUA BARAT | JS09 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
KLAYILI | PAPUA BARAT | JS107 | Talis5 Full | 2024-11-21 |  | vsat sudah up | 96.93% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 78.52%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
KAIREU | MALUKU | JS128 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
MITAK KOLAM | MALUKU | JS44 | Talis5 Mix | 2025-09-17 |  | SOMO POWER Done revit(17 sept 25) | 99.3% |  | 87.71% 1: 98.61%; 89.14% 2: 99.3%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 98.26%; 93.41% 6: 98.96%; 93.5% 7: 100%
ILILI | MALUKU | JS106 | Talis5 Full | 14 December 2024 |  | SNMP sudah up ( Done replace) | 99.95% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 99.65%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
KARUAN | PAPUA BARAT | JS24 | Talis5 Full | 6 sept 2025 |  | sudah up Done revit Talis5 Full ( tgl 6 sept 2025) | 99.55% |  | 87.71% 1: 96.88%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
MAIKOR | MALUKU | JS41 | JS PRO | 14 May 2025 |  | Site sudah up | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
TOSOA | MALUKU UTARA | JS122 | Talis5 Full | 19 October 2024 |  | VSAT sudah up | 99.83% |  | 87.71% 1: 100%; 89.14% 2: 99.83%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 98.96%; 93.41% 6: 100%; 93.5% 7: 100%
MAAN | PAPUA BARAT | JS74 | JS PRO |  | VSAT | VSAT sudah up, SNMP up . site masih down | 5.515% | Potensi SP | 87.71% 1: 3.539%; 89.14% 2: 3.471%; 90.1% 3: 9.655%; 89.69% 4: 7.011%; 91.27% 5: 10%; 93.41% 6: 4.927%; 93.5% 7: 0%
MIRAFAN | PAPUA BARAT | JS81 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
BEDARE | PAPUA BARAT | JS82 | Talis5 Full | 2024-11-16 |  |  | 96.48% |  | 87.71% 1: 95.83%; 89.14% 2: 95.83%; 90.1% 3: 96.53%; 89.69% 4: 97.22%; 91.27% 5: 95.83%; 93.41% 6: 96.53%; 93.5% 7: 97.57%
HUHUA | MALUKU | JS55 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SOFYANIN | MALUKU | JS48 | Talis5 Mix | 05 December 2024 |  |  | 99.9% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 99.3%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
NIJ | PAPUA BARAT | JS59 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SIRI-SIRI | PAPUA BARAT | JS85 | JS PRO |  |  | SNMP sudah up | 99.26% |  | 87.71% 1: 94.79%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SUNEI | PAPUA BARAT | JS35 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
KAINARA | MALUKU | JS22 | Talis5 Full | 2024-11-13 |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
UPT SP2 PATLEAN | MALUKU UTARA | JS121 | JS PRO |  |  |  | 99.4% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 95.83%; 93.41% 6: 100%; 93.5% 7: 100%
SUMANO | PAPUA BARAT | JS78 | Talis5 Full | 17 June 2025 |  | Vsat sudah up | 94.64% |  | 87.71% 1: 98.96%; 89.14% 2: 97.57%; 90.1% 3: 95.83%; 89.69% 4: 96.53%; 91.27% 5: 91.67%; 93.41% 6: 90.28%; 93.5% 7: 91.66%
SARIAI | PAPUA BARAT | JS29 | Talis5 Full | 2024-11-29 |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SUKOWATI | MALUKU | JS54 | Talis5 Mix | 13 August 2024 |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
AISANDAMI | PAPUA BARAT | JS36 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SERA | MALUKU | JS102 | Talis5 Full | 2024-11-20 |  | SNMP sudah up | 99.16% |  | 87.71% 1: 100%; 89.14% 2: 99.65%; 90.1% 3: 100%; 89.69% 4: 95.14%; 91.27% 5: 99.65%; 93.41% 6: 99.65%; 93.5% 7: 100%
MARFENFEN | MALUKU | JS18 | JS PRO |  | POWER | Low batt , masih down | 65.85% | Potensi SP | 87.71% 1: 0%; 89.14% 2: 0%; 90.1% 3: 60.92%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SANDEI | PAPUA BARAT | JS39 | Talis5 Full | 2024-11-19 |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
KAMAR | MALUKU | JS103 | Talis5 Mix | 2025-04-29 |  | VSAT SUDAH UP | 99.3% |  | 87.71% 1: 99.31%; 89.14% 2: 100%; 90.1% 3: 99.65%; 89.69% 4: 99.65%; 91.27% 5: 98.61%; 93.41% 6: 98.61%; 93.5% 7: 99.3%
WERLUMDITY | MALUKU | JS49 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
ATHABU | PAPUA BARAT | JS63 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
LILI | MALUKU UTARA | JS124 | JS PRO | 31 July 2025 |  | VSAT sudah up | 99.95% |  | 87.71% 1: 99.65%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
TOMARA | MALUKU UTARA | JS05 | Talis5 Full | 24 December 2024 |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
TEINEMAN | MALUKU | JS30 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
WAAN | PAPUA SELATAN | JS02 | JS PRO | 2025-11-14 |  | VSAT sudah up | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
BUMI RAHMAT | MALUKU UTARA | JS120 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
IMBU-IMBU | MALUKU UTARA | JS131 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
MUWINBOW | PAPUA BARAT | JS37 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
WOMBU | PAPUA BARAT | JS21 | JS PRO |  |  | SNMP flat (sudah normal) | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
DOROLAMO 1 | MALUKU UTARA | JS130 | JS PRO |  |  |  | 99.6% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 97.22%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
NONDANG | MALUKU UTARA | JS6 | Talis5 Mix | 28 December 2024 |  |  | 99.95% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 99.65%; 93.5% 7: 100%
SUMA TINGGI | MALUKU UTARA | JS15 | Talis5 Mix | 29 December 2024 | POWER-Tiket | SNMP sudh up done replace Ehub | 37.54% | Potensi SP | 87.71% 1: 0%; 89.14% 2: 0%; 90.1% 3: 0%; 89.69% 4: 0%; 91.27% 5: 62.75%; 93.41% 6: 100%; 93.5% 7: 100%
PURAGI | PAPUA BARAT | JS71 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SORRY | PAPUA BARAT | JS77 | JS PRO |  |  | vsat sudah up | 95.98% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 95.81%; 89.69% 4: 76.41%; 91.27% 5: 99.65%; 93.41% 6: 100%; 93.5% 7: 100%
SOSEPE | MALUKU UTARA | JS116 | JS PRO |  |  |  | 98.02% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 86.46%; 91.27% 5: 99.65%; 93.41% 6: 100%; 93.5% 7: 100%
SUMBER AGUNG | MALUKU | JS70 | JS PRO |  |  |  | 99.95% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 99.65%; 93.41% 6: 100%; 93.5% 7: 100%
TATANGAPU | MALUKU UTARA | JS126 | Talis5 Mix(migrasi pln) | 2025-11-08 |  | SOMO BTS Done revit 8-nov-25 | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
WASILEO | MALUKU UTARA | JS132 | JS PRO |  |  |  | 99.5% |  | 87.71% 1: 96.53%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
SAKETA | MALUKU UTARA | JS129 | JS PRO |  | POWER-Tiket | insiden terbakar site masih down | 0% | Potensi SP | bar: 87.71% 1 to 93.5% 7
KELO | MALUKU UTARA | JS118 | JS PRO |  |  |  | 100% |  | 87.71% 1: 100%; 89.14% 2: 100%; 90.1% 3: 100%; 89.69% 4: 100%; 91.27% 5: 100%; 93.41% 6: 100%; 93.5% 7: 100%
OHA | MALUKU UTARA | JS125 | JS PRO |  |  | Vsat up down | 89.29% |  | 87.71% 1: 91%; 89.14% 2: 95.83%; 90.1% 3: 60.76%; 89.69% 4: 92.36%; 91.27% 5: 92.71%; 93.41% 6: 100%; 93.5% 7: 92.36%

## siteinfo
SITE SUNDAYA PROJEK BAKTI TAHUN 2025
PROVINSI | TOTAL SITE | BATERAI | TOTAL SITE | LIST SITE
PAPUA | 35 | JS PRO | 20 | INYORA, RENIS, AISA, KOREWATARA, BORI, MAWE, BOLDON, SOBIAR, MAAN, MIRAFAN, NIJ, SIRI-SIRI, SUNEI, AISANDAMI, ATHABU, WAAN, MUWINBOW, WOMBU, PURAGI, SORRY
|  | TALIS5 FULL | 12 | ISENEBUAI, MAKARORO, NIAP, SOROWAN, SAYORI SIKAMA, NANIMORI, KLAYILI, KARUAN, BEDARE, SUMANO, SARIAI, SANDEI
|  | TALIS5 MIX | 3 | MENARBU, BOHA, YABORE
|  | TALIS5 MIX(MIGRASI PLN) | 0
MALUKU | 45 | JS PRO | 26 | SUMAE, OCIMALOLEO, WAYATIM, WARLOI, KAMPUNG BARU 1, SEKELY, TUTUPA, MARANTUTUL, TABAJAYA, KAIREU, MAIKOR, HUHUA, UPT SP2 PATLEAN, MARFENFEN, WERLUMDITY, LILI, TEINEMAN, BUMI RAHMAT, IMBU-IMBU, DOROLAMO 1, SOSEPE, SUMBER AGUNG, WASILEO, SAKETA, KELO, OHA
|  | TALIS5 FULL | 7 | KOBROR, RUMOY, ILILI, TOSOA, KAINARA, SERA, TOMARA
|  | TALIS5 MIX | 9 | HUKUKECIL, ELIASA, SILANG, MITAK KOLAM, SOFYANIN, SUKOWATI, KAMAR, NONDANG, SUMA TINGGI
|  | TALIS5 MIX(MIGRASI PLN) | 3 | TABANGAME, HONITETU, TATANGAPU
TOTAL | 80
BATERAI | TOTAL SITE | PERSENTASE
JS PRO | 46 | 57.5%
TALIS5 FULL | 19 | 42.5%
TALIS5 MIX | 12
TALIS5 MIX(MIGRASI PLN) | 3
TOTAL | 80

## Cluster
No | Provinsi | Kabupaten / Kota | No | Center Point
1 | Kepulauan Riau | Natuna | 1 | Natuna
|  | Kepulauan Anambas | 2 | Tarempa
2 | Maluku | Maluku Barat Daya | 3 | Wakpapapi/Saumlaki
Kepulauan Tanimbar
|  | Kepulauan Aru | 4 | Dobo
|  | Kepulauan Sula | 5 | Sanana
|  | Seram Bagian Timur | 6 | Bula
|  | Seram Bagian Barat | 7 | Ambon
3 | Maluku Utara | Halmahera Selatan | 8 | Ternate/Bacan
|  | Halmahera Timur | 9 | Haltim
Halmahera Barat
4 | Nusa Tenggara Timur | Kupang | 10 | Soe/Atambua
TOTAL NON PAPUA
1 | Papua Barat | Sorsel / sorong | 1 | Basecamp Kantor Sorong
|  |  | 2 | Teminabuan/Sorsel
|  |  | 3 | Maybrat
|  |  | 4 | Wondama &Mansel
2 | Papua | Mamberamo | 5 | Mamberamo/Srui
|  | Asmat | 6 | Asmat & Nduga
|  | Jayapura | 7 | Jayapura
|  |  | 8 | Merauke/Wamena
|  |  | 9 | Nabire

## Talis Full
19 | https://docs.google.com/spreadsheets/d/1Dxy1QCrdHtey6bTgAreH_-HSdvsVycgOWj8r7wFE9qo/edit?usp=sharing | [7 empty] | 89.04% | 92.46% | 93.09% | 92.87% | 93.48% | 94.02% | 94.15% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
NAMA SITE | PROVINSI | KODE SITE | BATERAI TYPE | Done Instal (Talis) | PIC | PROBLEM | SLA AVG | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
RUMOY | MALUKU | JS97 | Talis5 Full | 12 December 2024 | POWER-Tiket-onprogres | SNMP masih down | 0% | Potensi SP | bar: 1 to 7
MAKARORO | PAPUA BARAT | JS76 | Talis5 Full | 15 December 2024 | POWER | SNMP up down | 75.63% |  | 1: 0%; 2: 63.8%; 3: 100%; 4: 75.69%; 5: 89.93%; 6: 100%; 7: 100%
SUMANO | PAPUA BARAT | JS78 | Talis5 Full | 17 June 2025 |  | Vsat sudah up | 94.64% |  | 1: 98.96%; 2: 97.57%; 3: 95.83%; 4: 96.53%; 5: 91.67%; 6: 90.28%; 7: 91.66%
BEDARE | PAPUA BARAT | JS82 | Talis5 Full | 2024-11-16 |  |  | 96.48% |  | 1: 95.83%; 2: 95.83%; 3: 96.53%; 4: 97.22%; 5: 95.83%; 6: 96.53%; 7: 97.57%
KLAYILI | PAPUA BARAT | JS107 | Talis5 Full | 2024-11-21 |  | vsat sudah up | 96.93% |  | 1: 100%; 2: 100%; 3: 78.52%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SERA | MALUKU | JS102 | Talis5 Full | 2024-11-20 |  | SNMP sudah up | 99.16% |  | 1: 100%; 2: 99.65%; 3: 100%; 4: 95.14%; 5: 99.65%; 6: 99.65%; 7: 100%
KARUAN | PAPUA BARAT | JS24 | Talis5 Full | 6 sept 2025 |  | sudah up Done revit Talis5 Full ( tgl 6 sept 2025) | 99.55% |  | 1: 96.88%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
KOBROR | MALUKU | JS33 | Talis5 Full | 2025-10-06 |  | Done revit tgl 6/10/25 | 99.8% |  | 1: 100%; 2: 100%; 3: 98.61%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
TOSOA | MALUKU UTARA | JS122 | Talis5 Full | 19 October 2024 |  | VSAT sudah up | 99.83% |  | 1: 100%; 2: 99.83%; 3: 100%; 4: 100%; 5: 98.96%; 6: 100%; 7: 100%
ISENEBUAI | PAPUA BARAT | JS31 | Talis5 Full | 2024-11-30 |  | SNMP sudah up (Done replace ehub) | 99.9% |  | 1: 100%; 2: 100%; 3: 99.65%; 4: 100%; 5: 100%; 6: 100%; 7: 99.65%
ILILI | MALUKU | JS106 | Talis5 Full | 14 December 2024 |  | SNMP sudah up ( Done replace) | 99.95% |  | 1: 100%; 2: 100%; 3: 99.65%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
NIAP | PAPUA BARAT | JS26 | Talis5 Full | 04 August 2025 |  | SNMP sudah UP | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SOROWAN | PAPUA BARAT | JS89 | Talis5 Full | 14 December 2024 |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SAYORI SIKAMA | PAPUA BARAT | JS23 | Talis5 Full | 06 August 2025 |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
NANIMORI | PAPUA BARAT | JS11 | Talis5 Full | 10 August 2025 |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
KAINARA | MALUKU | JS22 | Talis5 Full | 2024-11-13 |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SARIAI | PAPUA BARAT | JS29 | Talis5 Full | 2024-11-29 |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SANDEI | PAPUA BARAT | JS39 | Talis5 Full | 2024-11-19 |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
TOMARA | MALUKU UTARA | JS05 | Talis5 Full | 24 December 2024 |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%

## Talis Mix
15 | https://docs.google.com/spreadsheets/d/1Dxy1QCrdHtey6bTgAreH_-HSdvsVycgOWj8r7wFE9qo/edit?usp=sharing |  |  |  | #DIV/0! |  |  |  | 78.89% | 79.81% | 83.87% | 83.07% | 85.3% | 92.11% | 93.26% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
NAMA SITE | PROVINSI | KODE SITE | BATERAI TYPE | Done Instal (Talis) | PIC | PROBLEM | SLA AVG | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
YABORE | PAPUA BARAT | JS17 | Talis5 Mix | 2025-10-06 | VSAT | VSAT masih down , Done revit tgl 6/10/25 | 0% | Potensi SP | bar: 1 to 7
SUMA TINGGI | MALUKU UTARA | JS15 | Talis5 Mix | 29 December 2024 | POWER-Tiket | SNMP sudh up done replace Ehub | 37.54% | Potensi SP | 1: 0%; 2: 0%; 3: 0%; 4: 0%; 5: 62.75%; 6: 100%; 7: 100%
HUKUKECIL | MALUKU | JS43 | Talis5 Mix | 2025-11-07 | VSAT | vsat sudh up | 45.45% | Potensi SP | 1: 0%; 2: 0%; 3: 58.43%; 4: 47.12%; 5: 25.79%; 6: 86.8%; 7: 100%
MENARBU | PAPUA BARAT | JS27 | Talis5 Mix | 2025-10-08 |  | Vsat up down | 96.38% |  | 1: 85.42%; 2: 97.91%; 3: 100%; 4: 100%; 5: 94.1%; 6: 97.57%; 7: 99.65%
MITAK KOLAM | MALUKU | JS44 | Talis5 Mix | 2025-09-17 |  | SOMO POWER Done revit(17 sept 25) | 99.3% |  | 1: 98.61%; 2: 99.3%; 3: 100%; 4: 100%; 5: 98.26%; 6: 98.96%; 7: 100%
KAMAR | MALUKU | JS103 | Talis5 Mix | 2025-04-29 |  | VSAT SUDAH UP | 99.3% |  | 1: 99.31%; 2: 100%; 3: 99.65%; 4: 99.65%; 5: 98.61%; 6: 98.61%; 7: 99.3%
SOFYANIN | MALUKU | JS48 | Talis5 Mix | 05 December 2024 |  |  | 99.9% |  | 1: 100%; 2: 100%; 3: 100%; 4: 99.3%; 5: 100%; 6: 100%; 7: 100%
NONDANG | MALUKU UTARA | JS6 | Talis5 Mix | 28 December 2024 |  |  | 99.95% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 99.65%; 7: 100%
BOHA | PAPUA SELATAN | JS01 | Talis5 Mix | 2025-11-13 |  | SOMO POWER , Vsat sudah up, SNMP problem. done revit tgl 13-nov-25 site up snmp sudah up | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
TABANGAME | MALUKU UTARA | JS13 | Talis5 Mix (Migrasi pln) | 2025-11-12 |  | SOMO BTS , power up down done revit tgl 12-nov-25 | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
ELIASA | MALUKU | JS34 | Talis5 Mix | 04 March 2025 |  | SNMP sudah up | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
HONITETU | MALUKU | JS42 | Talis5 Mix (Migrasi pln) | 2025-10-30 |  | SNMP sudah up | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SILANG | MALUKU UTARA | JS07 | Talis5 Mix | 16 January 2025 |  | SNMP sudah UP | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SUKOWATI | MALUKU | JS54 | Talis5 Mix | 13 August 2024 |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
TATANGAPU | MALUKU UTARA | JS126 | Talis5 Mix(migrasi pln) | 2025-11-08 |  | SOMO BTS Done revit 8-nov-25 | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%

## JS PRO
46 | https://docs.google.com/spreadsheets/d/1Dxy1QCrdHtey6bTgAreH_-HSdvsVycgOWj8r7wFE9qo/edit?usp=sharing |  |  |  | #DIV/0! |  |  |  | 90.05% | 90.81% | 90.89% | 90.53% | 92.31% | 93.59% | 93.3% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
NAMA SITE | PROVINSI | KODE SITE | BATERAI TYPE | Done Instal (Talis) | PIC | PROBLEM | SLA AVG | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
INYORA | PAPUA BARAT | JS19 | JS PRO |  | VSAT | VSAT masih down | 0% | Potensi SP | bar: 1 to 7
SAKETA | MALUKU UTARA | JS129 | JS PRO |  | POWER-Tiket | insiden terbakar site masih down | 0% | Potensi SP | bar: 1 to 7
MAAN | PAPUA BARAT | JS74 | JS PRO |  | VSAT | VSAT sudah up, SNMP up . site masih down | 5.515% | Potensi SP | 1: 3.539%; 2: 3.471%; 3: 9.655%; 4: 7.011%; 5: 10%; 6: 4.927%; 7: 0%
MARFENFEN | MALUKU | JS18 | JS PRO |  | POWER | Low batt , masih down | 65.85% | Potensi SP | 1: 0%; 2: 0%; 3: 60.92%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
RENIS | PAPUA BARAT | JS61 | JS PRO |  | VSAT | Vsat up down sudah stabil | 81.05% |  | 1: 60.11%; 2: 78.08%; 3: 79.21%; 4: 49.96%; 5: 100%; 6: 100%; 7: 100%
OCIMALOLEO | MALUKU UTARA | JS127 | JS PRO |  | VSAT | vsat sudah up | 88.19% |  | 1: 100%; 2: 100%; 3: 100%; 4: 65.56%; 5: 51.8%; 6: 100%; 7: 100%
OHA | MALUKU UTARA | JS125 | JS PRO |  |  | Vsat up down | 89.29% |  | 1: 91%; 2: 95.83%; 3: 60.76%; 4: 92.36%; 5: 92.71%; 6: 100%; 7: 92.36%
SORRY | PAPUA BARAT | JS77 | JS PRO |  |  | vsat sudah up | 95.98% |  | 1: 100%; 2: 100%; 3: 95.81%; 4: 76.41%; 5: 99.65%; 6: 100%; 7: 100%
BOLDON | PAPUA BARAT | JS86 | JS PRO |  |  | Vsat Sudah up | 96.97% |  | 1: 100%; 2: 100%; 3: 78.82%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SOSEPE | MALUKU UTARA | JS116 | JS PRO |  |  |  | 98.02% |  | 1: 100%; 2: 100%; 3: 100%; 4: 86.46%; 5: 99.65%; 6: 100%; 7: 100%
BORI | PAPUA BARAT | JS50 | JS PRO |  |  | Insiden Power Terbakar (Done donor), site sudah up | 98.07% |  | 1: 100%; 2: 100%; 3: 99.65%; 4: 86.8%; 5: 100%; 6: 100%; 7: 100%
SIRI-SIRI | PAPUA BARAT | JS85 | JS PRO |  |  | SNMP sudah up | 99.26% |  | 1: 94.79%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
UPT SP2 PATLEAN | MALUKU UTARA | JS121 | JS PRO |  |  |  | 99.4% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 95.83%; 6: 100%; 7: 100%
WASILEO | MALUKU UTARA | JS132 | JS PRO |  |  |  | 99.5% |  | 1: 96.53%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
TABAJAYA | MALUKU UTARA | JS14 | JS PRO |  |  |  | 99.55% |  | 1: 97.22%; 2: 100%; 3: 100%; 4: 100%; 5: 99.65%; 6: 100%; 7: 100%
DOROLAMO 1 | MALUKU UTARA | JS130 | JS PRO |  |  |  | 99.6% |  | 1: 100%; 2: 100%; 3: 97.22%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
TUTUPA | MALUKU UTARA | JS16 | JS PRO |  |  | VSAT sudah up | 99.8% |  | 1: 99.65%; 2: 100%; 3: 100%; 4: 100%; 5: 98.96%; 6: 100%; 7: 100%
SUMAE | MALUKU UTARA | JS12 | JS PRO |  |  | Vsat sudah up | 99.85% |  | 1: 100%; 2: 100%; 3: 98.96%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
AISA | PAPUA BARAT | JS69 | JS PRO |  |  | Vsat sudah up | 99.85% |  | 1: 99.65%; 2: 100%; 3: 100%; 4: 100%; 5: 99.3%; 6: 100%; 7: 100%
KOREWATARA | PAPUA BARAT | JS87 | JS PRO |  |  | SNMP sudah up | 99.9% |  | 1: 100%; 2: 99.65%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 99.65%
KAMPUNG BARU 1 | MALUKU UTARA | JS8 | JS PRO |  |  | SNMP sudah UP | 99.9% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 99.31%; 6: 100%; 7: 100%
MAWE | PAPUA BARAT | JS53 | JS PRO |  |  |  | 99.95% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 99.65%; 6: 100%; 7: 100%
MARANTUTUL | MALUKU | JS47 | JS PRO |  |  |  | 99.95% |  | 1: 100%; 2: 100%; 3: 100%; 4: 99.65%; 5: 100%; 6: 100%; 7: 100%
SUMBER AGUNG | MALUKU | JS70 | JS PRO |  |  |  | 99.95% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 99.65%; 6: 100%; 7: 100%
LILI | MALUKU UTARA | JS124 | JS PRO | 31 July 2025 |  | VSAT sudah up | 99.95% |  | 1: 99.65%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
WAYATIM | MALUKU UTARA | JS10 | JS PRO |  |  | Sudah up | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
WARLOI | MALUKU | JS28 | JS PRO |  |  | SNMP sudah up | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SEKELY | MALUKU UTARA | JS119 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SOBIAR | PAPUA BARAT | JS09 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
KAIREU | MALUKU | JS128 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
MAIKOR | MALUKU | JS41 | JS PRO | 14 May 2025 |  | Site sudah up | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
MIRAFAN | PAPUA BARAT | JS81 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
HUHUA | MALUKU | JS55 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
NIJ | PAPUA BARAT | JS59 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
SUNEI | PAPUA BARAT | JS35 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
AISANDAMI | PAPUA BARAT | JS36 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
WERLUMDITY | MALUKU | JS49 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
ATHABU | PAPUA BARAT | JS63 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
TEINEMAN | MALUKU | JS30 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
WAAN | PAPUA SELATAN | JS02 | JS PRO | 2025-11-14 |  | VSAT sudah up | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
BUMI RAHMAT | MALUKU UTARA | JS120 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
IMBU-IMBU | MALUKU UTARA | JS131 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
MUWINBOW | PAPUA BARAT | JS37 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
WOMBU | PAPUA BARAT | JS21 | JS PRO |  |  | SNMP flat (sudah normal) | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
PURAGI | PAPUA BARAT | JS71 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
KELO | MALUKU UTARA | JS118 | JS PRO |  |  |  | 100% |  | 1: 100%; 2: 100%; 3: 100%; 4: 100%; 5: 100%; 6: 100%; 7: 100%

## Potensi SP
https://docs.google.com/spreadsheets/d/1Dxy1QCrdHtey6bTgAreH_-HSdvsVycgOWj8r7wFE9qo/edit?usp=sharing
NAMA SITE | PROVINSI | KODE SITE | BATERAI TYPE | Done Instal (Talis) | PIC | PROBLEM | SLA AVG | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
YABORE | PAPUA BARAT | JS17 | Talis5 Mix | 2025-10-06 | VSAT | VSAT masih down , Done revit tgl 6/10/25 | 0% | Potensi SP | bar: 1 to 7
INYORA | PAPUA BARAT | JS19 | JS PRO |  | VSAT | VSAT masih down | 0% | Potensi SP | bar: 1 to 7
RUMOY | MALUKU | JS97 | Talis5 Full | 12 December 2024 | POWER-Tiket-onprogres | SNMP masih down | 0% | Potensi SP | bar: 1 to 7
SAKETA | MALUKU UTARA | JS129 | JS PRO |  | POWER-Tiket | insiden terbakar site masih down | 0% | Potensi SP | bar: 1 to 7
MAAN | PAPUA BARAT | JS74 | JS PRO |  | VSAT | VSAT sudah up, SNMP up . site masih down | 5.515% | Potensi SP | 1: 3.539%; 2: 3.471%; 3: 9.655%; 4: 7.011%; 5: 10%; 6: 4.927%; 7: 0%
SUMA TINGGI | MALUKU UTARA | JS15 | Talis5 Mix | 29 December 2024 | POWER-Tiket | SNMP sudh up done replace Ehub | 37.54% | Potensi SP | 1: 0%; 2: 0%; 3: 0%; 4: 0%; 5: 62.75%; 6: 100%; 7: 100%
HUKUKECIL | MALUKU | JS43 | Talis5 Mix | 2025-11-07 | VSAT | vsat sudh up | 45.45% | Potensi SP | 1: 0%; 2: 0%; 3: 58.43%; 4: 47.12%; 5: 25.79%; 6: 86.8%; 7: 100%
MARFENFEN | MALUKU | JS18 | JS PRO |  | POWER | Low batt , masih down | 65.85% | Potensi SP | 1: 0%; 2: 0%; 3: 60.92%; 4: 100%; 5: 100%; 6: 100%; 7: 100%

## Performa dibawah 95.5%
13 | https://docs.google.com/spreadsheets/d/1Dxy1QCrdHtey6bTgAreH_-HSdvsVycgOWj8r7wFE9qo/edit?usp=sharing
NAMA SITE | PROVINSI | KODE SITE | BATERAI TYPE | Done Instal (Talis) | PIC | PROBLEM | SLA AVG | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
RUMOY | MALUKU | JS97 | Talis5 Full | 12 December 2024 | POWER-Tiket-onprogres | SNMP masih down | 0% | Potensi SP | bar: 1 to 7
YABORE | PAPUA BARAT | JS17 | Talis5 Mix | 2025-10-06 | VSAT | VSAT masih down , Done revit tgl 6/10/25 | 0% | Potensi SP | bar: 1 to 7
INYORA | PAPUA BARAT | JS19 | JS PRO |  | VSAT | VSAT masih down | 0% | Potensi SP | bar: 1 to 7
SAKETA | MALUKU UTARA | JS129 | JS PRO |  | POWER-Tiket | insiden terbakar site masih down | 0% | Potensi SP | bar: 1 to 7
MAAN | PAPUA BARAT | JS74 | JS PRO |  | VSAT | VSAT sudah up, SNMP up . site masih down | 5.515% | Potensi SP | 1: 3.539%; 2: 3.471%; 3: 9.655%; 4: 7.011%; 5: 10%; 6: 4.927%; 7: 0%
SUMA TINGGI | MALUKU UTARA | JS15 | Talis5 Mix | 29 December 2024 | POWER-Tiket | SNMP sudh up done replace Ehub | 37.54% | Potensi SP | 1: 0%; 2: 0%; 3: 0%; 4: 0%; 5: 62.75%; 6: 100%; 7: 100%
HUKUKECIL | MALUKU | JS43 | Talis5 Mix | 2025-11-07 | VSAT | vsat sudh up | 45.45% | Potensi SP | 1: 0%; 2: 0%; 3: 58.43%; 4: 47.12%; 5: 25.79%; 6: 86.8%; 7: 100%
MARFENFEN | MALUKU | JS18 | JS PRO |  | POWER | Low batt , masih down | 65.85% | Potensi SP | 1: 0%; 2: 0%; 3: 60.92%; 4: 100%; 5: 100%; 6: 100%; 7: 100%
MAKARORO | PAPUA BARAT | JS76 | Talis5 Full | 15 December 2024 | POWER | SNMP up down | 75.63% |  | 1: 0%; 2: 63.8%; 3: 100%; 4: 75.69%; 5: 89.93%; 6: 100%; 7: 100%
RENIS | PAPUA BARAT | JS61 | JS PRO |  | VSAT | Vsat up down sudah stabil | 81.05% |  | 1: 60.11%; 2: 78.08%; 3: 79.21%; 4: 49.96%; 5: 100%; 6: 100%; 7: 100%
OCIMALOLEO | MALUKU UTARA | JS127 | JS PRO |  | VSAT | vsat sudah up | 88.19% |  | 1: 100%; 2: 100%; 3: 100%; 4: 65.56%; 5: 51.8%; 6: 100%; 7: 100%
OHA | MALUKU UTARA | JS125 | JS PRO |  |  | Vsat up down | 89.29% |  | 1: 91%; 2: 95.83%; 3: 60.76%; 4: 92.36%; 5: 92.71%; 6: 100%; 7: 92.36%
SUMANO | PAPUA BARAT | JS78 | Talis5 Full | 17 June 2025 |  | Vsat sudah up | 94.64% |  | 1: 98.96%; 2: 97.57%; 3: 95.83%; 4: 96.53%; 5: 91.67%; 6: 90.28%; 7: 91.66%

## Daily Dibawah 95.5%
LINK RAW DATA
https://docs.google.com/spreadsheets/d/1GFUfhivqP9iBBWcq2nUuYmIyrQoQL8pA3Nordh1HZQg/edit?usp=drive_link
SITE | BATERY | SLA DAILY | PROBLEM | SOLUSI | MITRA OM | NOTED
AISA | JS PRO | 74.695 |  |  | PAPUA BARAT | AISA JS PRO 74,695
MAWE | JS PRO | 100 |  |  | PAPUA BARAT | MAWE JS PRO 100
SIRI-SIRI | JS PRO | 100 |  |  | PAPUA BARAT | SIRI-SIRI JS PRO 100
NIAP | Talis5 Full | 36.854 |  |  | PAPUA BARAT | NIAP Talis5 Full 36,854
SUMAE | JS PRO | 0 |  |  | MALUKU UTARA | SUMAE JS PRO 0
KARUAN | JS PRO | 100 |  |  | PAPUA BARAT | KARUAN JS PRO 100
MITAK KOLAM | JS PRO | 100 |  |  | MALUKU | MITAK KOLAM JS PRO 100
SEKELY | JS PRO | 74.817 |  |  | MALUKU UTARA | SEKELY JS PRO 74,817
BOLDON | JS PRO | 74.697 |  |  | PAPUA BARAT | BOLDON JS PRO 74,697
SOROWAN | Talis5 Full | 78.819 |  |  | PAPUA BARAT | SOROWAN Talis5 Full 78,819
KOBROR | JS PRO | 74.673 |  |  | MALUKU | KOBROR JS PRO 74,673
HUKUKECIL | JS PRO | 0 |  |  | MALUKU | HUKUKECIL JS PRO 0
YABORE | JS PRO | 0 |  |  | PAPUA BARAT | YABORE JS PRO 0
ILILI | Talis5 Full | 100 |  |  | MALUKU | ILILI Talis5 Full 100
TUTUPA | JS PRO | 100 |  |  | MALUKU UTARA | TUTUPA JS PRO 100
WAYATIM | JS PRO | 74.73 |  |  | MALUKU UTARA | WAYATIM JS PRO 74,73
SAYORI SIKAMA | Talis5 Full | 100 |  |  | PAPUA BARAT | SAYORI SIKAMA Talis5 Full 100
NANIMORI | Talis5 Full | 74.993 |  |  | PAPUA BARAT | NANIMORI Talis5 Full 74,993
KOREWATARA | JS PRO | 74.699 |  |  | PAPUA BARAT | KOREWATARA JS PRO 74,699
MAKARORO | Talis5 Full | 100 |  |  | PAPUA BARAT | MAKARORO Talis5 Full 100
MARANTUTUL | JS PRO | 87.152 |  |  | MALUKU | MARANTUTUL JS PRO 87,152
TABAJAYA | JS PRO | 100 |  |  | MALUKU UTARA | TABAJAYA JS PRO 100
SOBIAR | JS PRO | 74.983 |  |  | PAPUA BARAT | SOBIAR JS PRO 74,983
KLAYILI | Talis5 Full | 100 |  |  | PAPUA BARAT | KLAYILI Talis5 Full 100
KAIREU | JS PRO | 61.971 |  |  | MALUKU | KAIREU JS PRO 61,971
BORI | JS PRO | 100 |  |  | PAPUA BARAT | BORI JS PRO 100
LILI | JS PRO | 100 |  |  | MALUKU UTARA | LILI JS PRO 100
TABANGAME | JS PRO | 68.394 |  |  | MALUKU UTARA | TABANGAME JS PRO 68,394
INYORA | JS PRO | 0 |  |  | PAPUA BARAT | INYORA JS PRO 0
KAMAR | Talis5 Mix | 100 |  |  | MALUKU | KAMAR Talis5 Mix 100
MAIKOR | JS PRO | 100 |  |  | MALUKU | MAIKOR JS PRO 100
OCIMALOLEO | JS PRO | 100 |  |  | MALUKU UTARA | OCIMALOLEO JS PRO 100
MENARBU | JS PRO | 94.79 |  |  | PAPUA BARAT | MENARBU JS PRO 94,79
RENIS | JS PRO | 100 |  |  | PAPUA BARAT | RENIS JS PRO 100
KAMPUNG BARU 1 | JS PRO | 49.672 |  |  | MALUKU UTARA | KAMPUNG BARU 1 JS PRO 49,672
MAAN | JS PRO | 98.958 |  |  | PAPUA BARAT | MAAN JS PRO 98,958
MIRAFAN | JS PRO | 74.716 |  |  | PAPUA BARAT | MIRAFAN JS PRO 74,716
BEDARE | Talis5 Full | 74.696 |  |  | PAPUA BARAT | BEDARE Talis5 Full 74,696
ELIASA | Talis5 Mix | 0 |  |  | MALUKU | ELIASA Talis5 Mix 0
HUHUA | JS PRO | 100 |  |  | MALUKU | HUHUA JS PRO 100
SOFYANIN | Talis5 Mix | 100 |  |  | MALUKU | SOFYANIN Talis5 Mix 100
NIJ | JS PRO | 100 |  |  | PAPUA BARAT | NIJ JS PRO 100
BOHA | JS PRO | 0 |  |  | PAPUA SELATAN | BOHA JS PRO 0
SUNEI | JS PRO | 100 |  |  | PAPUA BARAT | SUNEI JS PRO 100
HONITETU | JS PRO | 93.401 |  |  | MALUKU | HONITETU JS PRO 93,401
KAINARA | Talis5 Full | 100 |  |  | MALUKU | KAINARA Talis5 Full 100
UPT SP2 PATLEAN | JS PRO | 100 |  |  | MALUKU UTARA | UPT SP2 PATLEAN JS PRO 100
SUMANO | Talis5 Full | 74.98 |  |  | PAPUA BARAT | SUMANO Talis5 Full 74,98
SARIAI | Talis5 Full | 100 |  |  | PAPUA BARAT | SARIAI Talis5 Full 100
SUKOWATI | Talis5 Mix | 74.678 |  |  | MALUKU | SUKOWATI Talis5 Mix 74,678
AISANDAMI | JS PRO | 100 |  |  | PAPUA BARAT | AISANDAMI JS PRO 100
TOSOA | Talis5 Full | 73.087 |  |  | MALUKU UTARA | TOSOA Talis5 Full 73,087
SERA | Talis5 Full | 100 |  |  | MALUKU | SERA Talis5 Full 100
MARFENFEN | JS PRO | 100 |  |  | MALUKU | MARFENFEN JS PRO 100
WARLOI | JS PRO | 74.653 |  |  | MALUKU | WARLOI JS PRO 74,653
SANDEI | Talis5 Full | 74.982 |  |  | PAPUA BARAT | SANDEI Talis5 Full 74,982
SILANG | Talis5 Mix | 100 |  |  | MALUKU UTARA | SILANG Talis5 Mix 100
WERLUMDITY | JS PRO | 74.681 |  |  | MALUKU | WERLUMDITY JS PRO 74,681
ATHABU | JS PRO | 74.975 |  |  | PAPUA BARAT | ATHABU JS PRO 74,975
ISENEBUAI | Talis5 Full | 71.862 |  |  | PAPUA BARAT | ISENEBUAI Talis5 Full 71,862
TOMARA | Talis5 Full | 100 |  |  | MALUKU UTARA | TOMARA Talis5 Full 100
TEINEMAN | JS PRO | 61.892 |  |  | MALUKU | TEINEMAN JS PRO 61,892
RUMOY | Talis5 Full | 39.277 |  |  | MALUKU | RUMOY Talis5 Full 39,277
WAAN | JS PRO | 100 |  |  | PAPUA SELATAN | WAAN JS PRO 100
BUMI RAHMAT | JS PRO | 100 |  |  | MALUKU UTARA | BUMI RAHMAT JS PRO 100
IMBU-IMBU | JS PRO | 74.813 |  |  | MALUKU UTARA | IMBU-IMBU JS PRO 74,813
MUWINBOW | JS PRO | 78.819 |  |  | PAPUA BARAT | MUWINBOW JS PRO 78,819
WOMBU | JS PRO | 61.876 |  |  | PAPUA BARAT | WOMBU JS PRO 61,876
DOROLAMO 1 | JS PRO | 100 |  |  | MALUKU UTARA | DOROLAMO 1 JS PRO 100
NONDANG | Talis5 Mix | 74.996 |  |  | MALUKU UTARA | NONDANG Talis5 Mix 74,996
SUMA TINGGI | Talis5 Mix | 100 |  |  | MALUKU UTARA | SUMA TINGGI Talis5 Mix 100
PURAGI | JS PRO | 100 |  |  | PAPUA BARAT | PURAGI JS PRO 100
SORRY | JS PRO | 74.974 |  |  | PAPUA BARAT | SORRY JS PRO 74,974
SOSEPE | JS PRO | 49.82 |  |  | MALUKU UTARA | SOSEPE JS PRO 49,82
SUMBER AGUNG | JS PRO | 100 |  |  | MALUKU | SUMBER AGUNG JS PRO 100
TATANGAPU | JS PRO | 100 |  |  | MALUKU UTARA | TATANGAPU JS PRO 100
WASILEO | JS PRO | 100 |  |  | MALUKU UTARA | WASILEO JS PRO 100
SAKETA | JS PRO | 74.817 |  |  | MALUKU UTARA | SAKETA JS PRO 74,817
KELO | JS PRO | 77.083 |  |  | MALUKU UTARA | KELO JS PRO 77,083
OHA | JS PRO | 100 |  |  | MALUKU UTARA | OHA JS PRO 100

## SLA 2 SEPT
SITE | BATERY | PROBLEM | SLA | CONFIRM INTERNAL ANTRIAN DATA LOG SUNDAYA | FILE EXCEL